## Cover
Project Task Tracker
Plan, assign, and track every task in your project from start to completion.
HOW TO USE
1. Go to the Task Tracker tab and enter your project name and project manager at the top.
2. For each task, enter a task number, task name, project phase, and who it is assigned to.
3. Set the Priority (High, Medium, Low), start date, and due date.
4. Days Remaining calculates automatically from today. Overdue tasks show in red.
5. Update Status and percentage complete as work progresses.
6. The summary band at the top shows total tasks, completed, in progress, and overdue.
CLEARING THE SAMPLE DATA
The blue cells contain example data. Select them and press Delete to start with your own tasks. The white Days Remaining column looks after itself.
REMOVING THE FOOTER CREDIT
A small OpenSheets credit prints in the page footer. You are welcome to keep it. To remove it, go to Page Layout, then Page Setup, then the Header/Footer tab.
NOTES
Blue cells are your inputs. White cells are calculated. Do not type over the white cells. The sheet is protected so only blue cells can be edited.
Free template from
OpenSheets.co.uk
Professional spreadsheet templates for UK small businesses.
Going digital for Making Tax Digital?
aligned.tax
MTD for Income Tax bridging and compliance for sole traders and landlords.

## Task Tracker
Project Task Tracker | [6 empty] | Add your logo here
Project name: |  |  |  | Project manager:
TOTAL TASKS |  | COMPLETED |  | IN PROGRESS |  | OVERDUE
12 |  | 5 |  | 2 |  | 7
Task No | Task Name | Project / Phase | Assigned To | Priority | Start Date | Due Date | Days Remaining | Status | % Complete | Notes
T001 | Project kick-off meeting | Planning | Sarah Johnson | High | 2025-03-01 | 2025-03-05 |  | Complete | 100% | Meeting notes circulated
T002 | Requirements gathering | Planning | Mike Davies | High | 2025-03-05 | 2025-03-12 |  | Complete | 100% | Signed off by client
T003 | Design mockups | Design | Emma Wilson | High | 2025-03-13 | 2025-03-28 |  | Complete | 100% | Approved on 30/03
T004 | Front-end development | Development | Tom Harris | High | 2025-04-01 | 2025-04-30 |  | Complete | 100%
T005 | Back-end API | Development | Tom Harris | High | 2025-04-01 | 2025-05-15 | -406 | In progress | 75% | On track
T006 | Database setup | Development | Sarah Johnson | Medium | 2025-04-10 | 2025-04-20 |  | Complete | 100%
T007 | User testing | Testing | Emma Wilson | High | 2025-05-01 | 2025-05-20 | -401 | Not started | 0% | Waiting on T005
T008 | Bug fixes | Testing | Tom Harris | Medium | 2025-05-21 | 2025-06-05 | -385 | Not started | 0%
T009 | UAT sign-off | Testing | Mike Davies | High | 2025-06-06 | 2025-06-13 | -377 | Not started | 0%
T010 | Documentation | Documentation | Emma Wilson | Low | 2025-05-01 | 2025-05-31 | -390 | In progress | 40%
T011 | Deployment preparation | Deployment | Mike Davies | High | 2025-06-14 | 2025-06-20 | -370 | Not started | 0%
T012 | Go-live | Deployment | All team | High | 2025-06-23 | 2025-06-23 | -367 | Not started | 0% | Target date
Self-check: all task statuses add up to total tasks |  |  |  | OK - Balanced
Formulas:
Days Remaining = IF(OR([OVERDUE]="",[Status]="Complete",[Status]="Cancelled"),"",INT([OVERDUE]-TODAY()))